## PhD Timeline
Study/Task | Start Date | Finish Date | Duration (months) | Duration (weeks) | Days Until Start | Dependencies | Risks | Outputs | Status | Progress | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02 | 2026-06-09 | 2026-06-16 | 2026-06-23 | 2026-06-30 | 2026-07-07 | 2026-07-14 | 2026-07-21 | 2026-07-28 | 2026-08-04 | 2026-08-11 | 2026-08-18 | 2026-08-25 | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 2026-12-08 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-19 | 2027-01-26 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-02-23 | 2027-03-02 | 2027-03-09 | 2027-03-16 | 2027-03-23 | 2027-03-30 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-04-27 | 2027-05-04 | 2027-05-11 | 2027-05-18 | 2027-05-25 | 2027-06-01 | 2027-06-08 | 2027-06-15 | 2027-06-22 | 2027-06-29 | 2027-07-06 | 2027-07-13 | 2027-07-20 | 2027-07-27 | 2027-08-03 | 2027-08-10 | 2027-08-17 | 2027-08-24 | 2027-08-31 | 2027-09-07 | 2027-09-14 | 2027-09-21 | 2027-09-28 | 2027-10-05 | 2027-10-12 | 2027-10-19 | 2027-10-26 | 2027-11-02 | 2027-11-09 | 2027-11-16 | 2027-11-23 | 2027-11-30 | 2027-12-07 | 2027-12-14 | 2027-12-21 | 2027-12-28 | 2028-01-04 | 2028-01-11 | 2028-01-18 | 2028-01-25 | 2028-02-01 | 2028-02-08 | 2028-02-15 | 2028-02-22 | 2028-02-29 | 2028-03-07 | 2028-03-14 | 2028-03-21 | 2028-03-28 | 2028-04-04 | 2028-04-11 | 2028-04-18 | 2028-04-25 | 2028-05-02 | 2028-05-09 | 2028-05-16 | 2028-05-23 | 2028-05-30 | 2028-06-06 | 2028-06-13 | 2028-06-20 | 2028-06-27 | 2028-07-04 | 2028-07-11 | 2028-07-18 | 2028-07-25 | 2028-08-01 | 2028-08-08 | 2028-08-15 | 2028-08-22 | 2028-08-29 | 2028-09-05 | 2028-09-12 | 2028-09-19 | 2028-09-26 | 2028-10-03 | 2028-10-10 | 2028-10-17 | 2028-10-24 | 2028-10-31 | 2028-11-07 | 2028-11-14 | 2028-11-21 | 2028-11-28 | 2028-12-05 | 2028-12-12 | 2028-12-19 | 2028-12-26 | 2029-01-02 | 2029-01-09 | 2029-01-16 | 2029-01-23 | 2029-01-30 | 2029-02-06 | 2029-02-13 | 2029-02-20 | 2029-02-27 | 2029-03-06 | 2029-03-13 | 2029-03-20 | 2029-03-27 | 2029-04-03 | 2029-04-10 | 2029-04-17 | 2029-04-24 | 2029-05-01 | 2029-05-08 | 2029-05-15 | 2029-05-22 | 2029-05-29 | 2029-06-05 | 2029-06-12 | 2029-06-19 | 2029-06-26 | 2029-07-03 | 2029-07-10 | 2029-07-17 | 2029-07-24 | 2029-07-31 | 2029-08-07 | 2029-08-14 | 2029-08-21 | 2029-08-28 | 2029-09-04 | 2029-09-11 | 2029-09-18 | 2029-09-25 | 2029-10-02 | 2029-10-09 | 2029-10-16 | 2029-10-23 | 2029-10-30 | 2029-11-06 | 2029-11-13 | 2029-11-20 | 2029-11-27 | 2029-12-04 | 2029-12-11 | 2029-12-18 | 2029-12-25 | 2030-01-01 | 2030-01-08 | 2030-01-15 | 2030-01-22 | 2030-01-29 | 2030-02-05 | 2030-02-12 | 2030-02-19 | 2030-02-26 | 2030-03-05 | 2030-03-12 | 2030-03-19 | 2030-03-26 | 2030-04-02 | 2030-04-09 | 2030-04-16 | 2030-04-23 | 2030-04-30 | 2030-05-07 | 2030-05-14 | 2030-05-21 | 2030-05-28 | 2030-06-04 | 2030-06-11 | 2030-06-18 | 2030-06-25 | 2030-07-02 | 2030-07-09 | 2030-07-16 | 2030-07-23 | 2030-07-30 | 2030-08-06 | 2030-08-13 | 2030-08-20 | 2030-08-27 | 2030-09-03 | 2030-09-10 | 2030-09-17 | 2030-09-24 | 2030-10-01 | 2030-10-08 | 2030-10-15 | 2030-10-22 | 2030-10-29 | 2030-11-05 | 2030-11-12 | 2030-11-19 | 2030-11-26 | 2030-12-03 | 2030-12-10 | 2030-12-17 | 2030-12-24 | 2030-12-31 | 2031-01-07 | 2031-01-14 | 2031-01-21 | 2031-01-28 | 2031-02-04 | 2031-02-11 | 2031-02-18 | 2031-02-25 | 2031-03-04 | 2031-03-11 | 2031-03-18 | 2031-03-25 | 2031-04-01 | 2031-04-08 | 2031-04-15 | 2031-04-22 | 2031-04-29 | 2031-05-06 | 2031-05-13 | 2031-05-20 | 2031-05-27 | 2031-06-03 | 2031-06-10 | 2031-06-17 | 2031-06-24 | 2031-07-01 | 2031-07-08 | 2031-07-15 | 2031-07-22 | 2031-07-29 | 2031-08-05 | 2031-08-12 | 2031-08-19 | 2031-08-26 | 2031-09-02 | 2031-09-09 | 2031-09-16 | 2031-09-23 | 2031-09-30 | 2031-10-07 | 2031-10-14 | 2031-10-21 | 2031-10-28 | 2031-11-04 | 2031-11-11 | 2031-11-18 | 2031-11-25 | 2031-12-02 | 2031-12-09 | 2031-12-16 | 2031-12-23 | 2031-12-30 | 2032-01-06 | 2032-01-13 | 2032-01-20 | 2032-01-27 | 2032-02-03 | 2032-02-10 | 2032-02-17 | 2032-02-24 | 2032-03-02 | 2032-03-09 | 2032-03-16 | 2032-03-23 | 2032-03-30 | 2032-04-06 | 2032-04-13 | 2032-04-20 | 2032-04-27 | 2032-05-04 | 2032-05-11 | 2032-05-18 | 2032-05-25 | 2032-06-01 | 2032-06-08 | 2032-06-15 | 2032-06-22 | 2032-06-29 | 2032-07-06 | 2032-07-13 | 2032-07-20 | 2032-07-27 | 2032-08-03 | 2032-08-10 | 2032-08-17 | 2032-08-24 | 2032-08-31 | 2032-09-07 | 2032-09-14 | 2032-09-21 | 2032-09-28 | 2032-10-05 | 2032-10-12 | 2032-10-19 | 2032-10-26 | 2032-11-02 | 2032-11-09 | 2032-11-16 | 2032-11-23 | 2032-11-30 | 2032-12-07 | 2032-12-14 | 2032-12-21
CONFIRMATION MILESTONE
Prepare Timeline Document | 2025-08-25 | 2025-09-04 | 1 months | 2 weeks | Complete | None | Time needed to map out all studies comprehensively | Complete PhD timeline with Gantt chart | Confirmed | Complete | [45 empty] | 1 | 1 | 1
Draft Progress Report | 2025-09-01 | 2025-09-16 | 1 months | 3 weeks | Started 30 days ago | None | Balancing writing time with ongoing research | 10-page progress report | Confirmed | In Progress | [46 empty] | 1 | 1 | 1 | 1
Literature Review Update | 2025-09-01 | 2025-10-31 | 2 months | 9 weeks | Started 30 days ago | None | New publications emerging; refining scope | Updated literature review chapter | Confirmed | In Progress | [46 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Preliminary Results Summary | 2025-10-01 | 2025-12-31 | 3 months | 14 weeks | Today | Study 1 data available | Data collection timeline; analysis timeframe | Summary of preliminary findings | Confirmed | In Progress | [51 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Supervisor Review Meeting | 2026-01-01 | 2026-01-07 | 1 months | 1 weeks | 92 days | All documents drafted | Coordinating schedules; allowing time for feedback | Supervisor feedback and approval | Confirmed | In Progress | [64 empty] | 1 | 1
Revise Documents | 2026-01-08 | 2026-01-31 | 1 months | 4 weeks | 99 days | Supervisor feedback received | Scope of revisions needed | Final confirmation documents | Tentative | Not Started | [65 empty] | 1 | 1 | 1 | 1
Submit Confirmation Package | 2026-02-01 | 2026-02-07 | 1 months | 1 weeks | 123 days | All revisions complete | Processing timeframes | Submitted confirmation package | Tentative | Not Started | [68 empty] | 1 | 1
Confirmation Presentation | 2026-02-08 | 2026-02-08 | 1 months | 1 weeks | 130 days | Supervisor feedback following dry run | Preparation time needed; panel questions | Successful confirmation presentation | Confirmed | In Progress | [69 empty] | 1
STUDY 1: DELPHI STUDY (EXAMPLE)
Ethics Application | 2026-02-08 | 2026-04-30 | 3 months | 12 weeks | 130 days | None | Processing time; ensuring comprehensive documentation | Ethics approval granted | Tentative | Not Started | [69 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Panel Recruitment | 2026-05-01 | 2026-07-31 | 3 months | 14 weeks | 212 days | Ethics approval | Response rates; reaching diverse experts | Confirmed expert panel (n=15-20) | At Risk | In Progress | [81 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Round 1: Initial Survey | 2026-08-01 | 2026-09-30 | 2 months | 9 weeks | 304 days | Panel recruitment complete | Survey refinement needed; response timeframes | Round 1 survey responses; thematic analysis | Tentative | Not Started | [94 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Round 2: Consensus Building | 2026-10-01 | 2026-11-30 | 2 months | 9 weeks | Complete | Round 1 analysis complete | Time to achieve consensus; participant engagement | Round 2 responses; refined themes | Confirmed | Complete | [103 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Round 3 (if needed) | 2026-12-01 | 2027-01-31 | 2 months | 9 weeks | 426 days | Round 2 results | Additional round may extend timeline | Final consensus statements | Tentative | Not Started | [112 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Data Analysis | 2027-02-01 | 2027-03-31 | 2 months | 9 weeks | 488 days | All rounds complete | Integrating qualitative and quantitative findings | Thematic framework; consensus metrics | Tentative | Not Started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Write-up and Manuscript Draft | 2027-03-03 | 2027-06-02 | 3 months | 14 weeks | 518 days | Analysis complete | Identifying target journal; coordinating authorship | Draft manuscript for target journal | Tentative | Not Started | [125 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
OTHER PHD MILESTONES
Mid-Candidature Review | 2027-08-01 | 2027-08-31 | 1 months | 5 weeks | 669 days | At least 2 studies substantially progressed | Study completion timing; data collection pace | Mid-candidature approval | Tentative | Not Started | [146 empty] | 1 | 1 | 1 | 1 | 1 | 1
Pre-submission Seminar | 2029-01-02 | 2029-01-02 | 1 months | 1 weeks | 1189 days | Complete draft thesis | Ensuring coherence across studies | Faculty seminar presentation | Tentative | Not Started | [221 empty] | 1
Final Submission | 2029-03-02 | 2029-03-02 | 1 months | 1 weeks | 1248 days | Examined and revised thesis | Time for final revisions; formatting requirements | Submitted thesis | Tentative | Not Started | [229 empty] | 1
ADD YOUR STUDIES BELOW:
(Copy rows and edit - see Instructions)

## Instructions
RESEARCH TIMELINE PLANNER WITH GANTT CHART - INSTRUCTIONS
TIMELINE: Oct 2024 to Dec 2032 (430 weeks) - Extensible
✨ KEY FEATURES:
• WEEKLY GANTT CHART: Shows tasks week-by-week for precise timeline visualization
• AUTOMATIC DURATION: Calculates months between start/finish dates
• COLOR-CODED DURATION: Green (<3mo), Yellow (3-6mo), Orange (>6mo)
• COLOR-CODED STATUS: Risk level (Green=Confirmed, Yellow=Tentative, Red=At Risk)
• COLOR-CODED PROGRESS: Completion state (Grey=Not Started, Yellow=In Progress, Green=Complete)
• HIERARCHICAL PLANNING: Organize projects into milestones with subtasks
• CUSTOMIZABLE: Extend timeline, customize dropdowns, adapt to any field
═══════════════════════════════════════════════════════════════════════════════
NEW FEATURE: AUTOMATIC DURATION CALCULATION
═══════════════════════════════════════════════════════════════════════════════
The Duration column (D) automatically calculates the timespan of each task:
HOW IT WORKS:
• Counts complete months from Start Date to Finish Date
• Includes both the start and end months in the count
• Updates automatically when you change dates
• Displays as "X months" for easy reading
COLOR CODING:
• GREEN background = Short duration (1-2 months)
• LIGHT YELLOW background = Medium duration (3-6 months)
• LIGHT ORANGE background = Long duration (7+ months)
DURATION IN WEEKS (Column E):
• Calculates automatically from Start/Finish dates
• Shows duration as "X weeks"
• More precise than months for short tasks
• Color coded: Green (<4 weeks), Yellow (4-12 weeks), Orange (>12 weeks)
═══════════════════════════════════════════════════════════════════════════════
WEEKLY GANTT CHART RESOLUTION:
═══════════════════════════════════════════════════════════════════════════════
BENEFITS:
• See tasks shorter than 1 month with precision
• 3-week tasks show as 3 columns, not a full month
• Better visualization of overlapping tasks
• More accurate progress tracking
HEADER FORMAT:
• Each column = 1 week (starting on the date shown)
• Format: "DD-MMM" (e.g., "01-Oct", "08-Oct", "15-Oct")
• Columns are very narrow (1.8 width) to fit ~430 weeks on screen
HOW IT WORKS:
• Enter Start Date: 1/10/2024
• Enter Finish Date: 20/10/2024
• Gantt shows: 3 blue bars (weeks of Oct 1, Oct 8, Oct 15)
TIPS FOR WEEKLY PLANNING:
• Use specific day in month for Start/Finish dates
• Week starts on the date shown in header
• A bar appears if any part of that week overlaps with the task
• Scroll right to see the full ~8 year timeline
• For Status: Shows "Confirmed,Tentative,At Risk"
• For Progress: Shows "Not Started,In Progress,Complete"
• Edit the list: add, remove, or rename items (separate with commas)
STEP 4: Check "Apply these changes to all other cells with the same settings"
STEP 5: Click OK
STEP 6 (Optional): Update conditional formatting colors to match your new values
═══════════════════════════════════════════════════════════════════════════════
HOW TO EXTEND THE TIMELINE BEYOND 2032:
═══════════════════════════════════════════════════════════════════════════════
STEP 1: Select the last 12 Gantt columns (one year)
• Find column for Dec-32, hold SHIFT, click 11 columns left
STEP 2: Copy (Ctrl+C)
STEP 3: Click next empty column after Dec-32, Paste (Ctrl+V)
STEP 4: Fix header dates in row 1
• First new column: type 1/1/2033, formats as "Jan-33"
• Copy and drag right to auto-fill remaining months
STEP 5: Extend conditional formatting
• Home → Conditional Formatting → Manage Rules
• Find Gantt bar rule, edit "Applies to" range to include new columns
═══════════════════════════════════════════════════════════════════════════════
HOW TO EDIT DATES - IMPORTANT!
═══════════════════════════════════════════════════════════════════════════════
✓ CORRECT: Type "1/10/2025" (day/month/year) → displays as "Oct-25"
✓ CORRECT: Type "Oct 2025" → displays as "Oct-25"
✓ CORRECT: Type "1-Oct-2025" → displays as "Oct-25"
✗ AVOID: 31st for months with only 30 days (Apr, Jun, Sep, Nov)
✗ AVOID: 30th or 31st for February
💡 BEST PRACTICE: Always use 1st of the month (e.g., 1/10/2025 for October 2025)
When you update dates:
• Duration recalculates automatically
• Gantt chart bars update automatically
• Duration colors update based on new length
═══════════════════════════════════════════════════════════════════════════════
HOW TO ADD YOUR OWN STUDIES:
═══════════════════════════════════════════════════════════════════════════════
1. Copy an existing set of task rows
- Select an existing task row(s) → Copy (Ctrl+C)
- Click destination (ideally below 'ADD YOUR STUDIES BELOW:' row) → Right-click → Insert Copied Cells
2. Edit content with new study/milestone details
- All formulas (Duration and Gantt) adjust automatically
═══════════════════════════════════════════════════════════════════════════════
USE CASES:
═══════════════════════════════════════════════════════════════════════════════
This tool is ideal for:
• PhD/Masters Students: Confirmation planning, thesis chapters, multi-study programs
• Postdocs: Grant deliverables, multi-project coordination, paper timelines
• Research Teams: Collaborative projects, coordinating studies, lab milestones
• Supervisors: Monitoring student progress, planning lab activities
═══════════════════════════════════════════════════════════════════════════════
USING THE GANTT CHART:
═══════════════════════════════════════════════════════════════════════════════
• Blue bars show when each task occurs (by month)
• Scroll right to see full timeline (Oct 2024 - Dec 2032)
• Columns A-I frozen so you can see task details while scrolling
• Look for overlapping tasks to identify capacity issues
• Ensure dependent tasks flow sequentially
• Use Duration + Gantt together: number + visual
═══════════════════════════════════════════════════════════════════════════════
TROUBLESHOOTING:
═══════════════════════════════════════════════════════════════════════════════
GANTT BARS NOT SHOWING:
- Verify dates are valid (no 31/11 or 30/2)
- Check Start Date ≤ Finish Date
- Ensure dates formatted as MMM-YY
DURATION SHOWING ERROR:
- Check both Start and Finish dates are valid
- Make sure dates are actual Excel dates, not text
- Start Date must be before or equal to Finish Date
DURATION COLORS NOT SHOWING:
- Duration must display as "X months" format
- Check conditional formatting rules are active
- Formula may need refresh - try changing a date
DROPDOWN NOT APPEARING:
- Make sure clicking in column H (Status) or I (Progress)
- If missing, copy format from a working cell above
═══════════════════════════════════════════════════════════════════════════════
TECHNICAL DETAILS:
═══════════════════════════════════════════════════════════════════════════════
DURATION FORMULA: =IF(AND($B2<>"",$C2<>""),DATEDIF($B2,$C2,"M")+1&" months","")
• DATEDIF calculates complete months between dates
• +1 includes both start and end months
• &" months" formats as readable text
GANTT FORMULA: =IF(AND($B2<>"",$C2<>"",EOMONTH(COL$1,0)>=EOMONTH($B2,0),
EOMONTH(COL$1,0)<=EOMONTH($C2,0)),1,"")
• EOMONTH normalizes dates to month-end for comparison
• Compares timeline column date with task start/finish
• Returns 1 (colored blue) if month falls within task duration
CONDITIONAL FORMATTING:
• Duration: Based on extracted numeric value
• Status/Progress: Direct text match
• Gantt: Fills when cell value = 1
═══════════════════════════════════════════════════════════════════════════════
TIPS FOR SUCCESS:
═══════════════════════════════════════════════════════════════════════════════
• Use Duration colors to reality-check your timeline
• Update Progress regularly (grey → yellow → green as tasks complete)
• Update Status as uncertainties resolve (red/yellow → green)
• Review monthly with supervisors using Gantt visual
• Build in buffer time - add 20-30% to duration estimates
• Break very long tasks (>12 months) into subtasks
• Check for overlapping high-priority tasks (capacity planning)
• Keep it as a living document - update weekly/monthly!