## PhD Timeline
Study/Task | Start Date | Finish Date | Dependencies | Risks | Outputs | Status | Progress | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01 | 2030-04-01 | 2030-05-01 | 2030-06-01 | 2030-07-01 | 2030-08-01 | 2030-09-01 | 2030-10-01 | 2030-11-01 | 2030-12-01 | 2031-01-01 | 2031-02-01 | 2031-03-01 | 2031-04-01 | 2031-05-01 | 2031-06-01 | 2031-07-01 | 2031-08-01 | 2031-09-01 | 2031-10-01 | 2031-11-01 | 2031-12-01 | 2032-01-01 | 2032-02-01 | 2032-03-01 | 2032-04-01 | 2032-05-01 | 2032-06-01 | 2032-07-01 | 2032-08-01 | 2032-09-01 | 2032-10-01 | 2032-11-01 | 2032-12-01
CONFIRMATION MILESTONE
Prepare Timeline Document | 2025-08-01 | 2025-08-31 | None | Time needed to map out all studies comprehensively | Complete PhD timeline with Gantt chart | Tentative | Not Started | [10 empty] | 1
Draft Progress Report | 2025-08-01 | 2025-09-15 | None | Balancing writing time with ongoing research | 10-page progress report | Tentative | Not Started | [10 empty] | 1 | 1
Literature Review Update | 2025-08-01 | 2025-09-15 | None | New publications emerging; refining scope | Updated literature review chapter | Tentative | Not Started | [10 empty] | 1 | 1
Preliminary Results Summary | 2025-09-01 | 2025-09-30 | Study 1 data available | Data collection timeline; analysis timeframe | Summary of preliminary findings | Tentative | Not Started | [11 empty] | 1
Supervisor Review Meeting | 2025-10-01 | 2025-10-05 | All documents drafted | Coordinating schedules; allowing time for feedback | Supervisor feedback and approval | Tentative | Not Started | [12 empty] | 1
Revise Documents | 2025-10-06 | 2025-10-15 | Supervisor feedback received | Scope of revisions needed | Final confirmation documents | Tentative | Not Started | [12 empty] | 1
Submit Confirmation Package | 2025-10-16 | 2025-10-20 | All revisions complete | Processing timeframes | Submitted confirmation package | Tentative | Not Started | [12 empty] | 1
Confirmation Presentation | 2025-10-25 | 2025-10-25 | Package submitted | Preparation time needed; panel questions | Successful confirmation presentation | Tentative | Not Started | [12 empty] | 1
OTHER PHD MILESTONES
Mid-Candidature Review | 2026-10-01 | 2026-10-31 | At least 2 studies substantially progressed | Study completion timing; data collection pace | Mid-candidature approval | Tentative | Not Started | [24 empty] | 1
Pre-submission Seminar | 2028-01-01 | 2028-03-31 | Complete draft thesis | Ensuring coherence across studies | Faculty seminar presentation | Tentative | Not Started | [39 empty] | 1 | 1 | 1
Final Submission | 2028-10-01 | 2028-04-30 | Examined and revised thesis | Time for final revisions; formatting requirements | Submitted thesis | Tentative | Not Started
STUDY 1: DELPHI STUDY (EXAMPLE)
Panel Recruitment | 2024-11-01 | 2025-01-31 | Ethics approval | Response rates; reaching diverse experts | Confirmed expert panel (n=15-20) | Tentative | In Progress |  | 1 | 1 | 1
Round 1: Initial Survey | 2025-02-01 | 2025-03-31 | Panel recruitment complete | Survey refinement needed; response timeframes | Round 1 survey responses; thematic analysis | Tentative | Not Started |  |  |  |  | 1 | 1
Round 2: Consensus Building | 2025-04-01 | 2025-05-31 | Round 1 analysis complete | Time to achieve consensus; participant engagement | Round 2 responses; refined themes | Tentative | Not Started | [6 empty] | 1 | 1
Round 3 (if needed) | 2025-06-01 | 2025-07-31 | Round 2 results | Additional round may extend timeline | Final consensus statements | Tentative | Not Started | [8 empty] | 1 | 1
Data Analysis | 2025-08-01 | 2025-09-30 | All rounds complete | Integrating qualitative and quantitative findings | Thematic framework; consensus metrics | Tentative | Not Started | [10 empty] | 1 | 1
Write-up and Manuscript Draft | 2025-10-01 | 2025-12-31 | Analysis complete | Identifying target journal; coordinating authorship | Draft manuscript for target journal | Tentative | Not Started | [12 empty] | 1 | 1 | 1
ADD YOUR STUDIES BELOW:
(Copy rows and edit - see Instructions)

## Instructions
PhD CONFIRMATION TIMELINE WITH AUTOMATIC GANTT CHART - INSTRUCTIONS
TIMELINE: Oct 2024 to Dec 2032 (99 months)
DEADLINE: Please complete and submit by Friday next week
✨ KEY FEATURES:
• AUTOMATIC GANTT CHART: Changes when you update dates in columns B & C
• COLOR-CODED STATUS: Risk level (Green=Confirmed, Yellow=Tentative, Red=At Risk)
• COLOR-CODED PROGRESS: Completion state (Grey=Not Started, Yellow=In Progress, Green=Complete)
• CONFIRMATION BREAKDOWN: Detailed subtasks for reaching confirmation milestone
• CUSTOMIZABLE DROPDOWNS: Change dropdown values to match your needs (see instructions below)
═══════════════════════════════════════════════════════════════════════════════
DIFFERENCE BETWEEN STATUS AND PROGRESS:
═══════════════════════════════════════════════════════════════════════════════
STATUS (Column G) = Risk/Confidence Level:
• Confirmed (GREEN) - Dates firm, resources secured, everything lined up
• Tentative (YELLOW) - Dates approximate, some uncertainty remains
• At Risk (RED) - Significant blockers, may need intervention or adjustment
PROGRESS (Column H) = Completion State:
• Not Started (GREY) - Task not yet begun
• In Progress (YELLOW) - Currently working on this task
• Complete (GREEN) - Task finished and deliverables produced
Example: A task might be "Tentative" (unsure of timeline) but "In Progress" (already working on it)
═══════════════════════════════════════════════════════════════════════════════
HOW TO CUSTOMIZE DROPDOWN VALUES:
═══════════════════════════════════════════════════════════════════════════════
If you want to change the dropdown options (e.g., different status categories):
STEP 1: OPEN DATA VALIDATION
• Click on any cell with a dropdown (column G for Status, or H for Progress)
• Go to: Data tab → Data Validation (or Data Tools → Data Validation)
STEP 2: EDIT THE LIST
• In the dialog box, you will see "Source:" field
• For Status (column G): Shows "Confirmed,Tentative,At Risk"
• For Progress (column H): Shows "Not Started,In Progress,Complete"
• Edit this list: add, remove, or rename items (separate with commas, no spaces after commas)
• Example: Change to "Low,Medium,High,Critical" for Status
STEP 3: APPLY TO ALL CELLS
• Check the box "Apply these changes to all other cells with the same settings"
• Click OK
STEP 4: UPDATE CONDITIONAL FORMATTING (optional)
• If you changed the dropdown values, you may want to update the colors too
• Go to: Home → Conditional Formatting → Manage Rules
• Find rules for the column you changed (G or H)
• Click "Edit Rule" for each one
• Change the formula from (e.g.) ="Confirmed" to your new value like ="Low"
• You can also change the fill color in the Format button
• Click OK and Apply
TIP: If you just want to ADD a new option without removing existing ones,
add it to the end of the list: "Confirmed,Tentative,At Risk,On Hold"
═══════════════════════════════════════════════════════════════════════════════
HOW TO EXTEND THE TIMELINE BEYOND 2032:
═══════════════════════════════════════════════════════════════════════════════
If you need to extend the Gantt chart past December 2032, follow these steps:
STEP 1: SELECT THE LAST 12 GANTT COLUMNS (one year)
• Find the last month column (Dec-32) in the Gantt chart area
• Click on that column header letter
• Hold SHIFT and click 11 columns to the LEFT to select 12 months total
• You should have 12 columns highlighted (Jan-32 through Dec-32)
STEP 2: COPY THESE COLUMNS
• Press Ctrl+C (or right-click → Copy)
STEP 3: PASTE TO EXTEND
• Click on the NEXT EMPTY COLUMN header (right after Dec-32)
• Press Ctrl+V (or right-click → Paste)
• The formulas automatically adjust to the new columns!
• Repeat this step for each additional year you need
STEP 4: FIX THE HEADER DATES
• The pasted columns will have wrong dates in row 1
• Click the FIRST new header cell (row 1 of first pasted column)
• Type the next date: 1/1/2033 (for January 2033)
• Press Enter - it will format as "Jan-33"
• Now COPY this cell and DRAG RIGHT across the remaining new columns
• Excel will auto-increment: Jan-33, Feb-33, Mar-33, etc.
STEP 5: EXTEND THE CONDITIONAL FORMATTING
• Go to: Home tab → Conditional Formatting → Manage Rules
• Find the rule with blue fill (for Gantt bars)
• Click "Edit Rule"
• Look for "Applies to" field - it shows a range
• Change the END column letter to your new last column
• Click OK, then Apply
DONE! Test by changing a task date to fall in the new extended months.
═══════════════════════════════════════════════════════════════════════════════
HOW TO USE THE DROPDOWNS:
═══════════════════════════════════════════════════════════════════════════════
STATUS DROPDOWN (Column G - Risk Level):
1. Click on any Status cell
2. A dropdown arrow appears
3. Select: Confirmed (green), Tentative (yellow), or At Risk (red)
4. Cell automatically changes color!
PROGRESS DROPDOWN (Column H - Completion):
1. Click on any Progress cell
2. A dropdown arrow appears
3. Select: Not Started (grey), In Progress (yellow), or Complete (green)
4. Cell automatically changes color!
═══════════════════════════════════════════════════════════════════════════════
HOW TO EDIT DATES - IMPORTANT!
═══════════════════════════════════════════════════════════════════════════════
✓ CORRECT WAYS TO ENTER DATES:
- Type: "1/10/2025" (day/month/year) → displays as "Oct-25"
- Type: "Oct 2025" → displays as "Oct-25"
- Type: "1-Oct-2025" → displays as "Oct-25"
✗ AVOID INVALID DATES:
- DO NOT use 31st for months with only 30 days (Apr, Jun, Sep, Nov)
- DO NOT use 30th or 31st for February
💡 BEST PRACTICE: Always use 1st of the month
- October 2025 → "1/10/2025"
- November 2025 → "1/11/2025"
- February 2026 → "1/2/2026"
═══════════════════════════════════════════════════════════════════════════════
HOW TO ADD YOUR OWN STUDIES/MILESTONES/SUBTASKS:
═══════════════════════════════════════════════════════════════════════════════
1. Scroll to "ADD YOUR STUDIES BELOW" section
2. Insert a new row (right-click row number → Insert)
3. Add a STUDY HEADER (e.g., "STUDY 2: SLEEP DATA ANALYSIS")
- Leave dates blank for headers
4. Add subtask rows beneath:
- Task name in Column A
- Start/Finish Dates in Columns B & C (format: 1/10/2025)
- Dependencies, Risks, Outputs in columns D, E, F
- Select Status from dropdown in Column G
- Select Progress from dropdown in Column H
5. Gantt chart updates automatically!
COPYING ROWS:
- Select a task row → Copy (Ctrl+C)
- Click where you want it → Right-click → Insert Copied Cells
- Edit the details - formulas and dropdowns copy automatically
═══════════════════════════════════════════════════════════════════════════════
USING THE GANTT CHART:
═══════════════════════════════════════════════════════════════════════════════
• Blue bars show when each task occurs (by month)
• Scroll right to see full timeline (Oct 2024 - Dec 2032)
• Columns A-H are frozen so you can see task details while scrolling
• Look for overlapping tasks to identify capacity issues
• Ensure dependent tasks flow sequentially
• Use Status colors to spot risky tasks at a glance
• Use Progress colors to track completion state
═══════════════════════════════════════════════════════════════════════════════
TROUBLESHOOTING:
═══════════════════════════════════════════════════════════════════════════════
GANTT BARS NOT SHOWING:
- Verify dates are valid (no 31/11 or 30/2!)
- Check Start Date is before or equal to Finish Date
- Make sure dates are formatted correctly (MMM-YY display)
DROPDOWN NOT APPEARING:
- Make sure you are clicking in column G (Status) or H (Progress)
- The dropdown arrow appears when you click the cell
- If missing, copy format from a working cell above
COLORS NOT SHOWING:
- Make sure you typed or selected exactly the right value
- Check spelling and capitalization
- Try selecting from dropdown instead of typing
AFTER CHANGING DROPDOWN VALUES, COLORS STOPPED WORKING:
- You need to update the conditional formatting rules (see Step 4 above)
- The color rules are tied to the specific text values
═══════════════════════════════════════════════════════════════════════════════
FINAL TIPS:
═══════════════════════════════════════════════════════════════════════════════
• Update Progress regularly as you complete tasks (grey → yellow → green)
• Update Status as uncertainties resolve (red/yellow → green)
• Use both dimensions: a task can be "Confirmed" but "Not Started"
• Review this timeline with supervisors monthly
• Keep it as a living document!
• Customize the dropdown values to match your program requirements