## PhD Timeline
Study/Task | Start Date | Finish Date | Duration | Dependencies | Risks | Outputs | Status | Progress | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01 | 2030-04-01 | 2030-05-01 | 2030-06-01 | 2030-07-01 | 2030-08-01 | 2030-09-01 | 2030-10-01 | 2030-11-01 | 2030-12-01 | 2031-01-01 | 2031-02-01 | 2031-03-01 | 2031-04-01 | 2031-05-01 | 2031-06-01 | 2031-07-01 | 2031-08-01 | 2031-09-01 | 2031-10-01 | 2031-11-01 | 2031-12-01 | 2032-01-01 | 2032-02-01 | 2032-03-01 | 2032-04-01 | 2032-05-01 | 2032-06-01 | 2032-07-01 | 2032-08-01 | 2032-09-01 | 2032-10-01 | 2032-11-01 | 2032-12-01
CONFIRMATION MILESTONE
Prepare Timeline Document | 2025-08-01 | 2025-10-01 | 3 months | None | Time needed to map out all studies comprehensively | Complete PhD timeline with Gantt chart | Tentative | Not Started | [10 empty] | 1 | 1 | 1
Draft Progress Report | 2025-08-01 | 2025-09-15 | 2 months | None | Balancing writing time with ongoing research | 10-page progress report | Tentative | Not Started | [10 empty] | 1 | 1
Literature Review Update | 2025-08-01 | 2026-08-01 | 13 months | None | New publications emerging; refining scope | Updated literature review chapter | Tentative | Not Started | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Preliminary Results Summary | 2025-09-01 | 2025-09-30 | 1 months | Study 1 data available | Data collection timeline; analysis timeframe | Summary of preliminary findings | Tentative | Not Started | [11 empty] | 1
Supervisor Review Meeting | 2025-10-01 | 2025-10-05 | 1 months | All documents drafted | Coordinating schedules; allowing time for feedback | Supervisor feedback and approval | Tentative | Not Started | [12 empty] | 1
Revise Documents | 2025-10-06 | 2025-10-15 | 1 months | Supervisor feedback received | Scope of revisions needed | Final confirmation documents | Tentative | Not Started | [12 empty] | 1
Submit Confirmation Package | 2025-10-16 | 2025-10-20 | 1 months | All revisions complete | Processing timeframes | Submitted confirmation package | Tentative | Not Started | [12 empty] | 1
Confirmation Presentation | 2025-10-25 | 2025-10-25 | 1 months | Package submitted | Preparation time needed; panel questions | Successful confirmation presentation | Tentative | Not Started | [12 empty] | 1
OTHER PHD MILESTONES
Mid-Candidature Review | 2026-10-01 | 2026-10-31 | 1 months | At least 2 studies substantially progressed | Study completion timing; data collection pace | Mid-candidature approval | Tentative | Not Started | [24 empty] | 1
Pre-submission Seminar | 2028-01-01 | 2028-03-31 | 3 months | Complete draft thesis | Ensuring coherence across studies | Faculty seminar presentation | Tentative | Not Started | [39 empty] | 1 | 1 | 1
Final Submission | 2028-04-01 | 2028-10-31 | 7 months | Examined and revised thesis | Time for final revisions; formatting requirements | Submitted thesis | Tentative | Not Started | [42 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
STUDY 1: DELPHI STUDY (EXAMPLE)
Panel Recruitment | 2024-11-01 | 2025-01-31 | 3 months | Ethics approval | Response rates; reaching diverse experts | Confirmed expert panel (n=15-20) | Tentative | In Progress |  | 1 | 1 | 1
Round 1: Initial Survey | 2025-02-01 | 2025-03-31 | 2 months | Panel recruitment complete | Survey refinement needed; response timeframes | Round 1 survey responses; thematic analysis | Tentative | Not Started |  |  |  |  | 1 | 1
Round 2: Consensus Building | 2025-04-01 | 2025-05-31 | 2 months | Round 1 analysis complete | Time to achieve consensus; participant engagement | Round 2 responses; refined themes | Tentative | Not Started | [6 empty] | 1 | 1
Round 3 (if needed) | 2025-06-01 | 2025-07-31 | 2 months | Round 2 results | Additional round may extend timeline | Final consensus statements | Tentative | Not Started | [8 empty] | 1 | 1
Data Analysis | 2025-08-01 | 2025-09-30 | 2 months | All rounds complete | Integrating qualitative and quantitative findings | Thematic framework; consensus metrics | Tentative | Not Started | [10 empty] | 1 | 1
Write-up and Manuscript Draft | 2025-10-01 | 2025-12-31 | 3 months | Analysis complete | Identifying target journal; coordinating authorship | Draft manuscript for target journal | Tentative | Not Started | [12 empty] | 1 | 1 | 1
ADD YOUR STUDIES BELOW:
(Copy rows and edit - see Instructions)

## Instructions
RESEARCH TIMELINE PLANNER WITH GANTT CHART - INSTRUCTIONS
TIMELINE: Oct 2024 to Dec 2032 (99 months) - Extensible
✨ KEY FEATURES:
• AUTOMATIC GANTT CHART: Updates when dates change
• AUTOMATIC DURATION: Calculates months between start/finish dates
• COLOR-CODED DURATION: Green (<3mo), Yellow (3-6mo), Orange (>6mo)
• COLOR-CODED STATUS: Risk level (Green=Confirmed, Yellow=Tentative, Red=At Risk)
• COLOR-CODED PROGRESS: Completion state (Grey=Not Started, Yellow=In Progress, Green=Complete)
• HIERARCHICAL PLANNING: Organize projects into milestones with subtasks
• CUSTOMIZABLE: Extend timeline, customize dropdowns, adapt to any field
═══════════════════════════════════════════════════════════════════════════════
NEW FEATURE: AUTOMATIC DURATION CALCULATION
═══════════════════════════════════════════════════════════════════════════════
The Duration column (D) automatically calculates the timespan of each task:
HOW IT WORKS:
• Counts complete months from Start Date to Finish Date
• Includes both the start and end months in the count
• Updates automatically when you change dates
• Displays as "X months" for easy reading
COLOR CODING:
• GREEN background = Short duration (1-2 months)
• LIGHT YELLOW background = Medium duration (3-6 months)
• LIGHT ORANGE background = Long duration (7+ months)
TIPS:
• Use duration colors to spot unrealistic timelines at a glance
• Short tasks (<1 month) may indicate insufficient buffer time
• Very long tasks (>12 months) may need breaking into subtasks
• Check that total duration across studies fits within your program timeline
GANTT CHART INTEGRATION:
• The Gantt chart uses the same Start/Finish dates as Duration
• When you change a date, both Duration AND Gantt update automatically
• Duration gives you the number, Gantt gives you the visual
═══════════════════════════════════════════════════════════════════════════════
DIFFERENCE BETWEEN STATUS, PROGRESS & DURATION:
═══════════════════════════════════════════════════════════════════════════════
DURATION (Column D) = How long the task takes:
• Calculated automatically from dates
• Shows timespan in months
• Color-coded by length
STATUS (Column H) = Risk/Confidence Level:
• Confirmed (GREEN) - Dates firm, resources secured
• Tentative (YELLOW) - Dates approximate, some uncertainty
• At Risk (RED) - Significant blockers or challenges
PROGRESS (Column I) = Completion State:
• Not Started (GREY) - Task not yet begun
• In Progress (YELLOW) - Currently working on this
• Complete (GREEN) - Finished and deliverables produced
Example: A 6-month task might be "Tentative" (uncertain timeline) but "In Progress" (already started)
═══════════════════════════════════════════════════════════════════════════════
HOW TO CUSTOMIZE DROPDOWN VALUES:
═══════════════════════════════════════════════════════════════════════════════
If you want to change the dropdown options:
STEP 1: Click on any cell with a dropdown (column H for Status, or I for Progress)
STEP 2: Go to: Data tab → Data Validation
STEP 3: Edit the "Source:" field
• For Status (H): Shows "Confirmed,Tentative,At Risk"
• For Progress (I): Shows "Not Started,In Progress,Complete"
• Edit the list: add, remove, or rename items (separate with commas)
STEP 4: Check "Apply these changes to all other cells with the same settings"
STEP 5: Click OK
STEP 6 (Optional): Update conditional formatting colors to match your new values
═══════════════════════════════════════════════════════════════════════════════
HOW TO EXTEND THE TIMELINE BEYOND 2032:
═══════════════════════════════════════════════════════════════════════════════
STEP 1: Select the last 12 Gantt columns (one year)
• Find column for Dec-32, hold SHIFT, click 11 columns left
STEP 2: Copy (Ctrl+C)
STEP 3: Click next empty column after Dec-32, Paste (Ctrl+V)
STEP 4: Fix header dates in row 1
• First new column: type 1/1/2033, formats as "Jan-33"
• Copy and drag right to auto-fill remaining months
STEP 5: Extend conditional formatting
• Home → Conditional Formatting → Manage Rules
• Find Gantt bar rule, edit "Applies to" range to include new columns
═══════════════════════════════════════════════════════════════════════════════
HOW TO EDIT DATES - IMPORTANT!
═══════════════════════════════════════════════════════════════════════════════
✓ CORRECT: Type "1/10/2025" (day/month/year) → displays as "Oct-25"
✓ CORRECT: Type "Oct 2025" → displays as "Oct-25"
✓ CORRECT: Type "1-Oct-2025" → displays as "Oct-25"
✗ AVOID: 31st for months with only 30 days (Apr, Jun, Sep, Nov)
✗ AVOID: 30th or 31st for February
💡 BEST PRACTICE: Always use 1st of the month (e.g., 1/10/2025 for October 2025)
When you update dates:
• Duration recalculates automatically
• Gantt chart bars update automatically
• Duration colors update based on new length
═══════════════════════════════════════════════════════════════════════════════
HOW TO ADD YOUR OWN STUDIES:
═══════════════════════════════════════════════════════════════════════════════
1. Scroll to "ADD YOUR STUDIES BELOW"
2. Insert a new row (right-click row number → Insert)
3. Add a STUDY HEADER (e.g., "STUDY 2: SLEEP DATA ANALYSIS")
4. Add subtask rows beneath with:
- Task name (Column A)
- Start Date (Column B: format 1/10/2025)
- Finish Date (Column C: format 1/12/2025)
- Duration calculates automatically!
- Dependencies, Risks, Outputs (Columns E, F, G)
- Status dropdown (Column H)
- Progress dropdown (Column I)
5. Gantt chart updates automatically!
COPYING ROWS:
- Select a task row → Copy (Ctrl+C)
- Click destination → Right-click → Insert Copied Cells
- All formulas (Duration and Gantt) adjust automatically
═══════════════════════════════════════════════════════════════════════════════
USE CASES:
═══════════════════════════════════════════════════════════════════════════════
This tool is perfect for:
• PhD/Masters Students: Confirmation planning, thesis chapters, multi-study programs
• Postdocs: Grant deliverables, multi-project coordination, paper timelines
• Research Teams: Collaborative projects, coordinating studies, lab milestones
• Supervisors: Monitoring student progress, planning lab activities
═══════════════════════════════════════════════════════════════════════════════
USING THE GANTT CHART:
═══════════════════════════════════════════════════════════════════════════════
• Blue bars show when each task occurs (by month)
• Scroll right to see full timeline (Oct 2024 - Dec 2032)
• Columns A-I frozen so you can see task details while scrolling
• Look for overlapping tasks to identify capacity issues
• Ensure dependent tasks flow sequentially
• Use Duration + Gantt together: number + visual
═══════════════════════════════════════════════════════════════════════════════
TROUBLESHOOTING:
═══════════════════════════════════════════════════════════════════════════════
GANTT BARS NOT SHOWING:
- Verify dates are valid (no 31/11 or 30/2)
- Check Start Date ≤ Finish Date
- Ensure dates formatted as MMM-YY
DURATION SHOWING ERROR:
- Check both Start and Finish dates are valid
- Make sure dates are actual Excel dates, not text
- Start Date must be before or equal to Finish Date
DURATION COLORS NOT SHOWING:
- Duration must display as "X months" format
- Check conditional formatting rules are active
- Formula may need refresh - try changing a date
DROPDOWN NOT APPEARING:
- Make sure clicking in column H (Status) or I (Progress)
- If missing, copy format from a working cell above
═══════════════════════════════════════════════════════════════════════════════
TECHNICAL DETAILS:
═══════════════════════════════════════════════════════════════════════════════
DURATION FORMULA: =IF(AND($B2<>"",$C2<>""),DATEDIF($B2,$C2,"M")+1&" months","")
• DATEDIF calculates complete months between dates
• +1 includes both start and end months
• &" months" formats as readable text
GANTT FORMULA: =IF(AND($B2<>"",$C2<>"",EOMONTH(COL$1,0)>=EOMONTH($B2,0),
EOMONTH(COL$1,0)<=EOMONTH($C2,0)),1,"")
• EOMONTH normalizes dates to month-end for comparison
• Compares timeline column date with task start/finish
• Returns 1 (colored blue) if month falls within task duration
CONDITIONAL FORMATTING:
• Duration: Based on extracted numeric value
• Status/Progress: Direct text match
• Gantt: Fills when cell value = 1
═══════════════════════════════════════════════════════════════════════════════
TIPS FOR SUCCESS:
═══════════════════════════════════════════════════════════════════════════════
• Use Duration colors to reality-check your timeline
• Update Progress regularly (grey → yellow → green as tasks complete)
• Update Status as uncertainties resolve (red/yellow → green)
• Review monthly with supervisors using Gantt visual
• Build in buffer time - add 20-30% to duration estimates
• Break very long tasks (>12 months) into subtasks
• Check for overlapping high-priority tasks (capacity planning)
• Keep it as a living document - update weekly/monthly!